## CP-0260
LOS ANGELES COMMUNITY COLLEGE DISTRICT
DEPARTMENT OF FACILITIES PLANNING AND DEVELOPMENT
SUSTAINABLE BUILDING PROGRAM
CHANGE ORDER (CO)
DESIGN-BUILD & LEASE-LEASEBACK
Change Order No.:
DSA #03-
File #
PROJECT NAME: | [5 empty] | COLLEGE:
PROJECT NUMBER:
DESIGN-BUILDER/ CONTRACTOR NAME:
PURCHASE ORDER / CONTRACT NUMBER: | [6 empty] | DATE:
The Contract is changed as follows: |  |  | n | Pre-Construction / Design Services (Non-DSA) Amount: |  |  |  |  | 0
|  |  | n | Construction Services (DSA) Amount: |  |  |  |  | 0
The Contract is changed as follows:
n | Original Contract Sum: | [7 empty] | 0
n | Net change by previously authorized Change Orders: | [7 empty] | 0
n | Contract Sum prior to this Change Order: | [7 empty] | 0
n | Contract Sum will be
| by this Change Order in the amount of: | [7 empty] | 0
n | New Contract Sum including this Change Order: | [7 empty] | 0
| n | Contract Pre-Construction / Design Services (Non-DSA) Amount:
| n | Contract Construction Services (DSA) Amount:
n | Total Change Orders to this Contract: | [7 empty] | 0
n | Change Order % of the original contract amount | [7 empty] | #DIV/0!
The Contract Time will be: (if "unchanged" enter "0") | [7 empty] | by Days:
The Contract Milestones will be changed due to this Change Order:
The date of Substantial Completion as of the date of this Change Order therefore is/remains:
The funding source for this Change Order is:
Contractor must sign and return this Change Order by (date): |  |  |  | 1900-01-09 | (10 days from date CO issued to Contractor)
Should the Contractor fail to sign and return this Change Order as requested, the Owner reserves the right to process the Change Order unilaterally without the Contractor's signature. If this Change Order is being issued unilaterally, check the box below.
This Change Order is being issued as a Unilateral Change Order by the District
NOTE: In accordance with the provisions of Articles 4.4 and 7.4 of the General Conditions, failure by the Contractor to submit a timely and proper Claim after issuance of a Unilateral Change Order by the District constitutes a waiver by the Contractor of its right to further recourse or recovery, either by means of the Claims Dispute Resolution Process or by any other legal process otherwise provided for under Applicable Laws, based on an assertion that the amount of the contract adjustment on account of the change or delay described in such change order proposal, change order request, or otherwise, should be different than the amount of the contract adjustment set forth in such Unilateral Change Order.
NOTE: By the execution of this Change Order, all parties accept the Contract Sum change and the change in the date of Substantial Completion, if any, and expressly waive any claims for any additional compensation, damages, or time extensions not included in this document, in connection with the above referenced changes.
Design-Builder/Contractor Firm (Print Name & Company) |  |  |  | Signature |  |  |  |  | Date
Dr. Rueben Smith
LACCD Chief Facilities Executive or Director of Facilities Planning & Development (Print Name) |  |  |  | Signature |  |  |  |  | Date
CHANGE ORDER DOCUMENT ROUTING SHEET
(Routing sheet is not be mailed with executed document - attach only to file copy)
College Project Team Manager (Print Name) |  |  |  | Signature |  |  |  |  | Date
College Project Director (Print Name) |  |  |  | Signature |  |  |  |  | Date
College President (Print Name) |  |  |  | Signature |  |  |  |  | Date
Regional Program Director (RPD) (Print Name) |  |  |  | Signature |  |  |  |  | Date
PMO Program Controls (Print Name) |  |  |  | Signature |  |  |  |  | Date
PMO Program Director (Print Name) |  |  |  | Signature |  |  |  |  | Date
Increased
Decreased
Unchanged
Increased
Decreased
Unchanged
Yes
No
Prop A
Prop AA
Measure J
Measure CC

## PRECON-DES SUMMARY
LOS ANGELES COMMUNITY COLLEGE DISTRICT
DEPARTMENT OF FACILITIES PLANNING AND DEVELOPMENT
SUSTAINABLE BUILDING PROGRAM
DESIGN-BUILD & LEASE-LEASEBACK CHANGE ORDER REQUEST SUMMARY
Change Order No.: |  |  | 0
| DSA #03- |  | 0
| File # |  | 0
| PROJECT NAME: |  | 0 |  |  | COLLEGE: |  | 0
| PROJECT NUMBER: |  | 0
| DESIGN BUILD / CONTRACTOR NAME: |  | 0
| PURCHASE ORDER / CONTRACT NUMBER: |  | 0 |  |  |  | DATE: | 0
PRE-CONSTRUCTION / DESIGN SERVICES
COR # |  | COR Date | COR Description |  |  |  |  | Reason Code | Additive COR Cost | Deductive COR Cost (enter as negative number)
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[6 empty] | Additive COR's this Change Order: |  |  |  | 0
[6 empty] | Deductive COR's this Change Order: |  |  |  | 0
[6 empty] | Net COR's this Change Order: |  |  |  | 0
PRE-CONSTRUCTION / DESIGN SERVICES SUMMARY
Legend: Reason Code (RC) |  |  |  | Additive Totals | Deductive Totals | Net Totals
1 | Owner Requested Change in Scope of Work: |  |  | 0 | 0 | 0
2 | Unforeseen Condition Changes: |  |  | 0 | 0 | 0
3 | Design Related Changes: |  |  | 0 | 0 | 0
4 | Code/Agency Required Changes: |  |  | 0 | 0 | 0

## CONST SUMMARY
LOS ANGELES COMMUNITY COLLEGE DISTRICT
DEPARTMENT OF FACILITIES PLANNING AND DEVELOPMENT
SUSTAINABLE BUILDING PROGRAM
DESIGN-BUILD & LEASE-LEASEBACK CHANGE ORDER REQUEST SUMMARY
Change Order No.: |  |  | 0
| DSA #03- |  | 0
| File # |  | 0
| PROJECT NAME: |  | 0 |  |  | COLLEGE: |  | 0
| PROJECT NUMBER: |  | 0
| DESIGN BUILD / CONTRACTOR NAME: |  | 0
| PURCHASE ORDER / CONTRACT NUMBER: |  | 0 |  |  |  | DATE: | 0
CONSTRUCTION SERVICES
COR # |  | COR Date | COR Description |  |  |  |  | Reason Code | Additive COR Cost | Deductive COR Cost (enter as negative number)
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[6 empty] | Additive COR's this Change Order: |  |  |  | 0
[6 empty] | Deductive COR's this Change Order: |  |  |  | 0
[6 empty] | Net COR's this Change Order: |  |  |  | 0
CONSTRUCTION SERVICES SUMMARY
Legend: Reason Code (RC) |  |  |  | Additive Totals | Deductive Totals | Net Totals
1 | Owner Requested Change in Scope of Work: |  |  | 0 | 0 | 0
2 | Unforeseen Condition Changes: |  |  | 0 | 0 | 0
3 | Design Related Changes: |  |  | 0 | 0 | 0
4 | Code/Agency Required Changes: |  |  | 0 | 0 | 0

## JUSTIFICATION
LOS ANGELES COMMUNITY COLLEGE DISTRICT
DEPARTMENT OF FACILITIES PLANNING AND DEVELOPMENT
SUSTAINABLE BUILDING PROGRAM
Change Order Justification Form
DESIGN-BUILD & LEASE-LEASEBACK CHANGE ORDER (CO)
DATE: | 0 |  | COLLEGE: | 0 |  | CPT - PROJECT MANAGER:
PROJECT NAME: | 0 |  |  |  |  | PROJECT NO.: | 0 |  |  | CONTRACT NO.: |  | 0
CONTRACTOR NAME: | 0 |  |  |  |  | Change Order Amount: |  | 0 |  | Change Order Days: |  | 0
Change Order No.: | 0 |  |  |  |  | Change Percentage (to date) |  |  | #DIV/0! | % Owner
Original Contract Sum: |  | 0 |  |  |  | Change Percentage (to date) |  |  | #DIV/0! | % Design / Code/Agency
[6 empty] | Change Percentage (to date) |  |  | #DIV/0! | % Unforeseen
Previously Executed Change Order Amount: |  |  |  | 0 |  | Current Change Order Amount: |  |  | 0
Project is: |  | % | complete as of (date): |  |  |  |  | Revised date of Project Substantial Completion: |  |  | 0
Indicate the amount and percentage of this Change Orders attributable to:
PRE-CONSTRUCTION / DESIGN SERVICES (Not including previous change orders) | [6 empty] | CONSTRUCTION SERVICES (Not including previous change orders)
CURRENT CHANGE ORDER AMOUNT AND PERCENTAGE | [5 empty] | % of Original Contract | CURRENT CHANGE ORDER AMOUNT AND PERCENTAGE |  |  |  |  | % of Original Contract
Additive Owner Requested Changes: |  |  |  | 0 | --- | #DIV/0! | Additive Owner Requested Changes: |  |  | 0 | --- | #DIV/0!
Additive Unforeseen Condition Changes: |  |  |  | 0 | --- | #DIV/0! | Additive Unforeseen Condition Changes: |  |  | 0 | --- | #DIV/0!
Additive Design Related Changes: |  |  |  | 0 | --- | #DIV/0! | Additive Design Related Changes: |  |  | 0 | --- | #DIV/0!
Additive Code/Agency Required Changes: |  |  |  | 0 | --- | #DIV/0! | Additive Code/Agency Required Changes: |  |  | 0 | --- | #DIV/0!
Deductive Owner Requested Changes: |  |  |  | 0 | --- | #DIV/0! | Deductive Owner Requested Changes: |  |  | 0 | --- | #DIV/0!
Deductive Unforeseen Condition Changes: |  |  |  | 0 | --- | #DIV/0! | Deductive Unforeseen Condition Changes: |  |  | 0 | --- | #DIV/0!
Deductive Design Related Changes: |  |  |  | 0 | --- | #DIV/0! | Deductive Design Related Changes: |  |  | 0 | --- | #DIV/0!
Deductive Code/Agency Required Changes: |  |  |  | 0 | --- | #DIV/0! | Deductive Code/Agency Required Changes: |  |  | 0 | --- | #DIV/0!
Total Owner Requested Changes: |  |  |  | 0 | --- | #DIV/0! | TotalOwner Requested Changes: |  |  | 0 | --- | #DIV/0!
Total Unforeseen Changes: |  |  |  | 0 | --- | #DIV/0! | Total Unforeseen Changes: |  |  | 0 | --- | #DIV/0!
Total Design Related Changes: |  |  |  | 0 | --- | #DIV/0! | Total Design Related Changes: |  |  | 0 | --- | #DIV/0!
Total Code/Agency Required Changes: |  |  |  | 0 | --- | #DIV/0! | Total Code/Agency Required Changes: |  |  | 0 | --- | #DIV/0!
Indicate the amount and percentage of this Change Orders attributable to: | [6 empty] | Indicate the amount for "PREVIOUS" Contract Change Orders attributable to:
CURRENT CHANGE ORDER SUMMARY (Not including previous change orders) | [6 empty] | PREVIOUS CHANGE ORDER SUMMARY (Not including current change orders)
CURRENT CHANGE ORDER AMOUNT AND PERCENTAGE | [5 empty] | % of Original Contract | TOTAL PREVIOUS CHANGE ORDERS
Additive Owner Requested Changes: |  |  |  | 0 | --- | #DIV/0! | Additive Owner Requested Changes: |  |  | 0 | --- | #DIV/0!
Additive Unforeseen Condition Changes: |  |  |  | 0 | --- | #DIV/0! | Additive Unforeseen Condition Changes: |  |  | 0 | --- | #DIV/0!
Additive Design Related Changes: |  |  |  | 0 | --- | #DIV/0! | Additive Design Related Changes: |  |  | 0 | --- | #DIV/0!
Additive Code/Agency Required Changes: |  |  |  | 0 | --- | #DIV/0! | Additive Code/Agency Required Changes: |  |  | 0 | --- | #DIV/0!
Deductive Owner Requested Changes: |  |  |  | 0 | --- | #DIV/0! | Deductive Owner Requested Changes: |  |  | 0 | --- | #DIV/0!
Deductive Unforeseen Condition Changes: |  |  |  | 0 | --- | #DIV/0! | Deductive Unforeseen Condition Changes: |  |  | 0 | --- | #DIV/0!
Deductive Design Related Changes: |  |  |  | 0 | --- | #DIV/0! | Deductive Design Related Changes: |  |  | 0 | --- | #DIV/0!
Deductive Code/Agency Required Changes: |  |  |  | 0 | --- | #DIV/0! | Deductive Code/Agency Required Changes: |  |  | 0 | --- | #DIV/0!
Total Owner Requested Changes: |  |  |  | 0 | --- | #DIV/0! | Total Owner Requested Changes: |  |  | 0 | --- | #DIV/0!
Total Unforeseen Changes: |  |  |  | 0 | --- | #DIV/0! | Total Unforeseen Changes: |  |  | 0 | --- | #DIV/0!
Total Design Related Changes: |  |  |  | 0 | --- | #DIV/0! | Total Design Related Changes: |  |  | 0 | --- | #DIV/0!
Total Code/Agency Required Changes: |  |  |  | 0 | --- | #DIV/0! | Total Code/Agency Required Changes: |  |  | 0 | --- | #DIV/0!
Explain why these conditions were not considered in the original Contract Documents
Describe all known future changes for Owner Requested Changes to the original Contract Documents
Describe all known future changes for Unforeseen Condition Changes to the original Contract Documents
Describe all known future changes for Design Related Changes to the original Contract Documents
Describe all known future changes for Code/Agency Required Changes to the original Contract Documents
Additional Explanations or Comments:
College Project Director (Signature) | [5 empty] | Name (Print Name) |  |  |  |  | Date