## CO MEMO (COVER PAGE)
LOS ANGELES COMMUNITY COLLEGE DISTRICT
DEPARTMENT OF FACILITIES PLANNING AND DEVELOPMENT
SUSTAINABLE BUILDING PROGRAM
MEMO FOR RECORD - CHANGE ORDER (CO)
Date: |  | 0
College: |  | 0
Project Name: |  | 0
Contractor Name: |  | 0
Architect Name: |  | 0
Delivery Method: |  | Design-Bid-Build
Contract / PO #: |  | 0
Subject: | Change Order No.
Contract Time: |  |  |  |  | 0 | days
Original Contract Sum: |  |  |  | 0
Change Order Amount: |  |  |  | 0 |  |  | Legend: Reason Code (RC)
Change Order % of the Original Amount Less DCPC: |  |  |  | #DIV/0! |  |  | 1 | Owner Requested Change in Scope of Work
Target Board of Trustees (BOT) Approval Date: | [6 empty] | 2 | Unforeseen Condition Changes
Issued as Unilateral Change Order by the District: |  |  |  | No |  |  | 3 | Design Related Changes
[7 empty] | 4 | Code/Agency Required Changes
Remaining DCPC amount after this Change Order: |  |  |  | N/A |  |  | 5 | Return of Unused Allowance/Contingency
Total % of DCPC Remaining after this Change Order: |  |  |  | N/A
Additional Notes: |  | N/A
This Change Order includes the following work:
COR No. | COR Amount |  | COR Description | [5 empty] | RC
Enter Target BOT Approval Date and complete all Form CP-0261 tabs.
The information on the Memo for Record, including the COR Lists, will autopopulate from their respective tabs. Additional Notes may be entered (Defaulted as 'N/A').
Delete Unused Rows:
> Left-click the row number(s) (on the left edge
of your screen) to select the entire row(s).
> Right-click the row number and select
'Delete'.

## CP-0261 CO DBB
LOS ANGELES COMMUNITY COLLEGE DISTRICT
DEPARTMENT OF FACILITIES PLANNING AND DEVELOPMENT
SUSTAINABLE BUILDING PROGRAM
CHANGE ORDER (CO)
DESIGN-BID-BUILD
Change Order No.: |  |  |  | DSA #03- |  |  |  | File #
PROJECT NAME: | [7 empty] | COLLEGE:
PROJECT NUMBER:
CONTRACTOR NAME:
ARCHITECT FIRM NAME:
PURCHASE ORDER / CONTRACT NUMBER: | [7 empty] | DATE: |  |  | DCPC
FALSE
The Contract is changed as follows:
n | Original Contract Award Amount: | [8 empty] | 0
| • Total Amount of Accepted Base Bid + Allowances + Non-DCPC Contingency: | [5 empty] | 0
| • District Controlled Project Contingency (DCPC) Amount, if applicable: | [5 empty] | 0
n | Net change by previously authorized Change Orders, not including DCPC: | [8 empty] | 0
n | Contract Sum prior to this Change Order: | [8 empty] | 0
n | Contract Sum will be |  | unchanged |  | by this Change Order in the amount of: |  |  |  |  | 0
n | New Contract Sum including this Change Order: | [8 empty] | 0
n | Total Change Orders to this Contract: | [8 empty] | 0
n | Change Order % of the Original Contract Award Amount Less DCPC Amount: | [8 empty] | #DIV/0!
DCPC Summary: |  | Total DCPC amount applied to previously authorized Change Orders: | [7 empty] | N/A
|  | Total DCPC amount applied to this Change Order: | [7 empty] | N/A
|  | Remaining DCPC amount after this Change Order: | [7 empty] | N/A
|  |  | Total % of DCPC Remaining after this Change Order: | [6 empty] | N/A | Increased | Decreased | Unchanged
The Contract Time will be: (if "unchanged" enter "0") | [8 empty] | by Days: |  | FALSE | FALSE | FALSE
The Contract Milestones will be changed due to this Change Order:
The date of Substantial Completion as of the date of this Change Order therefore is/remains:
The funding source for this Change Order is:
Contractor must sign and return this Change Order by (date): |  |  |  |  | 1900-01-09 | (10 days from date CO issued to Contractor)
Should the Contractor fail to sign and return this Change Order as requested, the Owner reserves the right to process the Change Order unilaterally without the Contractor's signature. If this Change Order is being issued unilaterally, check the box below. | [10 empty] | Unilateral
This Change Order is being issued as a Unilateral Change Order by the District | [10 empty] | FALSE
NOTE: In accordance with the provisions of Articles 4.4 and 7.4 of the General Conditions, failure by the Contractor to submit a timely and proper Claim after issuance of a Unilateral Change Order by the District constitutes a waiver by the Contractor of its right to further recourse or recovery, either by means of the Claims Dispute Resolution Process or by any other legal process otherwise provided for under Applicable Laws, based on an assertion that the amount of the contract adjustment on account of the change or delay described in such change order proposal, change order request, or otherwise, should be different than the amount of the contract adjustment set forth in such Unilateral Change Order.
NOTE: By the execution of this Change Order, all parties accept the Contract Sum change and the change in the date of Substantial Completion, if any, and expressly waive any claims for any additional compensation, damages, or time extensions not included in this document, in connection with the above referenced changes.
Design-Builder/Contractor Firm (Print Name & Company) |  |  |  |  | Signature |  |  |  |  | Date
Dr. Rueben Smith
LACCD Chief Facilities Executive or Director of Facilities Planning & Development (Print Name) |  |  |  |  | Signature |  |  |  |  | Date
CHANGE ORDER DOCUMENT ROUTING SHEET
(Routing sheet is not be mailed with executed document - attach only to file copy)
AOR / Design Consultant Firm (Print Name & Company) |  |  |  |  | Signature |  |  |  |  | Date
College Project Team Manager (Print Name) |  |  |  |  | Signature |  |  |  |  | Date
College Project Director (Print Name) |  |  |  |  | Signature |  |  |  |  | Date
College President (Print Name) |  |  |  |  | Signature |  |  |  |  | Date
Regional Program Director (RPD) (Print Name) |  |  |  |  | Signature |  |  |  |  | Date
PMO Program Controls (Print Name) |  |  |  |  | Signature |  |  |  |  | Date
PMO Program Director (Print Name) |  |  |  |  | Signature |  |  |  |  | Date
Increased
Decreased
Unchanged
Yes
No
Prop A
Prop AA
Measure J
Measure CC
District Controlled Project Contingency (DCPC) applies to the total amount of this CO

## CP-0261 SUMMARY
LOS ANGELES COMMUNITY COLLEGE DISTRICT
DEPARTMENT OF FACILITIES PLANNING AND DEVELOPMENT
SUSTAINABLE BUILDING PROGRAM
DESIGN-BID-BUILD CHANGE ORDER REQUEST SUMMARY
Change Order No.: |  |  | 0
| DSA #03- |  | 0
| File # |  | 0
| PROJECT NAME: |  | 0 |  |  | COLLEGE: |  | 0
| PROJECT NUMBER: |  | 0
| CONTRACTOR NAME: |  | 0
| PO / CONTRACT NO.: |  | 0 |  |  |  | DATE: | 0
COR # |  | COR Date | COR Description |  |  |  |  | Reason Code | Additive COR Cost | Deductive COR Cost (enter as negative number)
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[6 empty] | Additive COR's this Change Order: |  |  |  | 0
[6 empty] | Deductive COR's this Change Order: |  |  |  | 0
[6 empty] | Net COR's this Change Order: |  |  |  | 0
SUMMARY
Legend: Reason Code (RC) |  |  |  | Additive Totals | Deductive Totals | Net Totals
1 | Owner Requested Change in Scope of Work: |  |  | 0 | 0 | 0
2 | Unforeseen Condition Changes: |  |  | 0 | 0 | 0
3 | Design Related Changes: |  |  | 0 | 0 | 0
4 | Code/Agency Required Changes: |  |  | 0 | 0 | 0
5 | Return of Unused Allowance/Contingency |  |  | 0 | 0 | 0

## CP-0261 JUSTIFICATION
LOS ANGELES COMMUNITY COLLEGE DISTRICT
DEPARTMENT OF FACILITIES PLANNING AND DEVELOPMENT
SUSTAINABLE BUILDING PROGRAM
Change Order Justification Form
DESIGN-BID-BUILD CHANGE ORDER (CO)
DATE: | 0 |  | COLLEGE: | 0 |  |  | CPT - PROJECT MANAGER:
PROJECT NAME: | 0 | [5 empty] | PROJECT NO.: | 0 |  |  | PURCHASE ORDER / CONTRACT NO.: |  |  | 0
CONTRACTOR NAME: | 0 | [5 empty] | Change Order Amount: |  | 0 |  | Change Order Days: |  |  | 0
Change Order No.: | 0 | [5 empty] | Change Percentage (to date) |  |  | #DIV/0! | % Owner
Original Contract Award Amount Less DCPC Amount: | [6 empty] | Change Percentage (to date) |  |  | #DIV/0! | % Design / Code/Agency
|  | 0 |  |  |  |  | Change Percentage (to date) |  |  | #DIV/0! | % Unforeseen
Previously Executed Change Order Amount: (Not including District Controlled Project Contingency) |  |  |  | 0 |  |  | Current Change Order Amount: |  |  | 0
Project is: |  | % | complete as of (date): | [5 empty] | Revised date of Project Substantial Completion: |  |  |  | 0
Indicate the amount and percentage of this Change Orders attributable to: | [7 empty] | Indicate the amount for "PREVIOUS" Contract Change Orders attributable to:
CURRENT CHANGE ORDER SUMMARY (Not including previous change orders) | [7 empty] | PREVIOUS CHANGE ORDER SUMMARY (Not including current change orders)
CURRENT CHANGE ORDER AMOUNT AND PERCENTAGE |  |  |  |  | % of Original Contract Award Less DCPC |  |  | TOTAL PREVIOUS CHANGE ORDERS (Not including District Controlled Project Contingency) |  |  |  | % of Original Contract Award Less DCPC
Additive Owner Requested Changes: |  |  |  | 0 |  | --- | #DIV/0! | Additive Owner Requested Changes: |  |  | 0 |  | --- | #DIV/0!
Additive Unforeseen Condition Changes: |  |  |  | 0 |  | --- | #DIV/0! | Additive Unforeseen Condition Changes: |  |  | 0 |  | --- | #DIV/0!
Additive Design Related Changes: |  |  |  | 0 |  | --- | #DIV/0! | Additive Design Related Changes: |  |  | 0 |  | --- | #DIV/0!
Additive Code/Agency Required Changes: |  |  |  | 0 |  | --- | #DIV/0! | Additive Code/Agency Required Changes: |  |  | 0 |  | --- | #DIV/0!
Additive Return Unused Allowance/Contingency: |  |  |  | 0 |  | --- | #DIV/0! | Additive Return Unused Allowance/Contingency: |  |  | 0 |  | --- | #DIV/0!
Deductive Owner Requested Changes: |  |  |  | 0 |  | --- | #DIV/0! | Deductive Owner Requested Changes: |  |  | 0 |  | --- | #DIV/0!
Deductive Unforeseen Condition Changes: |  |  |  | 0 |  | --- | #DIV/0! | Deductive Unforeseen Condition Changes: |  |  | 0 |  | --- | #DIV/0!
Deductive Design Related Changes: |  |  |  | 0 |  | --- | #DIV/0! | Deductive Design Related Changes: |  |  | 0 |  | --- | #DIV/0!
Deductive Code/Agency Required Changes: |  |  |  | 0 |  | --- | #DIV/0! | Deductive Code/Agency Required Changes: |  |  | 0 |  | --- | #DIV/0!
Deductive Return Unused Allowance/Contingency |  |  |  | 0 |  | --- | #DIV/0! | Deductive Return Unused Allowance/Contingency |  |  | 0 |  | --- | #DIV/0!
Total Owner Requested Changes: |  |  |  | 0 |  | --- | #DIV/0! | Total Owner Requested Changes: |  |  | 0 |  | --- | #DIV/0!
Total Unforeseen Changes: |  |  |  | 0 |  | --- | #DIV/0! | Total Unforeseen Changes: |  |  | 0 |  | --- | #DIV/0!
Total Design Related Changes: |  |  |  | 0 |  | --- | #DIV/0! | Total Design Related Changes: |  |  | 0 |  | --- | #DIV/0!
Total Code/Agency Required Changes: |  |  |  | 0 |  | --- | #DIV/0! | Total Code/Agency Required Changes: |  |  | 0 |  | --- | #DIV/0!
Total Return Unused Allowance/Contingency |  |  |  | 0 |  | --- | #DIV/0! | Total Return Unused Allowance/Contingency |  |  | 0 |  | --- | #DIV/0!
Explain why these conditions were not considered in the original Contract Documents
Describe all known future changes for Owner Requested Changes to the original Contract Documents
Describe all known future changes for Unforeseen Condition Changes to the original Contract Documents
Describe all known future changes for Design Related Changes to the original Contract Documents
Describe all known future changes for Code/Agency Required Changes to the original Contract Documents
Additional Explanations or Comments:
Name (Print Name) | [6 empty] | College Project Director (Signature) | [5 empty] | Date

## Drop down menus (hidden)
Los Angeles City College
East Los Angeles College
Los Angeles Harbor College
Los Angeles Mission College
Los Angeles Pierce College
Los Angeles Southwest College
Los Angeles Trade Tech College
Los Angeles Valley College
West Los Angeles College
Design Build (DB)
Lease-Leaseback (LLB)